## APP-GN97-GFU (hidden)
PUBLIC PROCUREMENT REGULATORY AUTHORITY
Guidelines on Filling the Procurement Plan Template for Goods, Works and Non-Consultancy Services
1. | An Annual Procurement Plan (APP) is a mandatory feature of the procurement policy framework as articulated in PPA 2004. The approval of APP in a Management Meeting of a PE which is chaired by the Accounting Officer or Chief Executive Officer can be used to achieve the requirement that all procurement must have the approval of the Accounting Officer or Chief Executive Officer. It can further be used as a monitoring tool to ensure that all planned procurement follow set procedures and target dates.
2. | The Procurement Plan Template for Goods, Works and Non-Consultancy Services has been prepared to fulfill the requirements of Section 45 of the PPA 2004 and Regulations 40, 46 and 47 of GN. 97 of 2005.
3. | Three kinds of APP Templates are introduced in this Guideline as shown below. A Soft Copy of the Guideline is contained in a Worksheet designated as APP-GN97-GFU.
| 3.1 | Template of APP for Internal Use: This Template is contained in a Worksheet designated as APP-GN97-IU. It gives detailed information about each procurement to be carried out by a PE including key dates for which certain actions must be completed by its staff to ensure that there is no delay in the procurement process. For each tender, two rows are provided: one for recording the planned dates for various actions and one for filling in actual dates when the actions were implemented.
| 3.2 | Template of APP for External Use: This Template is contained in a Worksheet designated as APP-GN97-EU. It gives detailed information about each procurement to be carried out by a PE through open competition and it forms part of the GPN to be made available to potential bidders. It aims at notifying potential bidders of procurement opportunities available in a PE. In this template information regarding particulars of tender, dates for advertisement and notification of bidders are given.
| 3.3 | Template of APP for Submission to PPRA: This Template is contained in a Worksheet designated as APP-GN97-PPRA. It gives detailed information about each procurement to be carried out by a PE including key dates for notifying potential bidders of the tender proceedings and results of the tender process. This is required to be submitted to PPRA at the start of the financial year to enable PPRA be aware of the procurement volume for that particular year and enable it plan its monitoring activities accordingly.
4. | Abbreviations used in this Guideline
| APP | Annual Procurement Plan
| GN.97 | The Public Procurement (Goods, Works, Non-Consultancy Services, and Disposal of Public Assets by Tender) Regulations, GN. No. 97 of 2005
| GPN | General Procurement Notice
| PE | Procuring Entity
| PMU | Procurement Management Unit
| PPA 2004 | Public Procurement Act No. 21 of 2004
| PPRA | Public Procurement Regulatory Authority
| TB | Tender Board
Column No. | Guidance on the Information to be filled in the respective column of the Template |  | Corresponding Column in the APP Template for External Use | Corresponding Column in the APP Template for Submission to PPRA
01-06 | These columns gives details of various tenders to be floated by the PE, their estimated values and selected procurement methods |  | 01-04 | 01-04
01. | This column shall include a brief description of the Tender e.g. Tender for the Supply of Office Stationery |  | 01 | 01
02. | This column shall include the designated tender number. For easy identification of the PEs, PPRA shall issue code numbers to identify each PE. The tender number shall be preceded by the code number of the PE and the respective financial year. For example, if the code number of the PE is P01 and the financial year is 2006/7, the tender numbers shall be preceded by P01-2006/7- |  | 02 | 02
03. | This column shall indicate lot numbers in case of a tender divided into lots. When there is only one lot, this shall be shown in this column as a single lot. |  | 03 | 03
04. | This column shall indicate the estimated value of the procurement for each lot. The estimated value shall to a large extent reflect the budgeted amount for that procurement. To assist PEs to prepare correct estimates, the Research and Documentation Section of PPRA shall prepare price indices for various items based on tenders carried out in the previous years. |  | This information is not required for disclosure to the potential bidders as it will tend to influence prices | 04
05. | Procurement method to be adopted shall be shown in this column. Determination of the appropriate method shall be guided by Part VI - Methods of procurement and their conditions for use of the GN. 97. |  | 04 | 05
06. | For tenders where open tendering methods have been found to be appropriate, they shall be advertised in the GPN. The date earmarked for the GPN shall be shown in this column. To cut down on the costs of advertising, the PE should consider using a minimum number of GPN consisting of several tenders. |  | This is not required since the whole of this document consist GPN | 06
07-12 | These columns apply for Tenders where pre-qualification of bidders need to be carried out prior to inviting tenders. |  | 05-07 | 07-09
07. | In this column, the PE shall indicate the deadline by which pre-qualification documents must be ready for approval in order to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
08. | This column indicates the deadline by which pre-qualification documents must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. The approval of the documents can be delegated to the PMU.
09. | This column shall indicate the date when the PE expects to advertise for the pre-qualification process. |  | 05 | 07
10. | This column shall indicate the expected deadline for the submission and opening of the pre-qualification entries. Statutory periods from the date of advertising to the submission of the applications are given in the Third Schedule of GN. 97. They are 30 days and 21 days for the international and national competitive bidding respectively. |  | 06 | 08
11. | In this column, the PE shall indicate the deadline by which the evaluation of pre-qualification entries must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
12. | This column indicates the deadline by which the pre-qualification evaluation report must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. This shall also be the date for notifications of the outcome of the pre-qualification process. |  | 07- The successful applicants must be immediately be informed after the approval of shortlist is done by the TB | 09
13-18 | These columns gives the details of the actual tender process starting from the preparation of bidding documents to the approval of award of contract. |  | 08-10 | 10-13
13. | In this column, the PE shall indicate the deadline by which the Tender Document must be ready for approval in order to ensure that subsequent stages of the procurement are not affected.This deadline may be in parallel with deadlines for actions under columns 07 to 12. |  | This information is for internal use to the PE
14. | This column indicates the deadline by which the Tender Document must be approved by the TB in order to ensure that subsequent stages of the procurement are not affected. The approval of the document can be delegated to the PMU. In cases of tenders with pre-qualification, in order to avoid delays, this date could the same as that appearing in column 12
15. | This column shall indicate the date when the PE expects to advertise for the tender or to start to issue tender documents to the shortlisted bidders in the case of a tender with pre-qualification. |  | 08 | 10
16. | This column shall indicate the expected deadline for the submission and opening of the tenders. Statutory periods from the date of advertising to the submission of tenders are given in the Third Schedule of GN. 97. They are 45 days and 30 days for the international and national competitive bidding respectively. |  | 09 | 12
17. | In this column, the PE shall indicate the deadline by which the evaluation of tenders must be completed to ensure that subsequent stages of the procurement are not affected.. |  | This information is for internal use to the PE
18. | This column indicates the deadline by which the tender evaluation report must be approved by the TB. This shall also be the date for notifying the winner. |  | 10- The successful bidder must immediately be informed after the approval of contract award is done by the TB | 13
19-21 | These columns gives the details of the final actions towards formalization of the contract.
19. | In this column the amount of the contract award shall be inserted. In the planned row it is expected to insert the estimated (budgeted amount) of the particular tender. In the actual row PE shall insert the amount of the contract award approved by the TB |  | This information is for internal use to the PE. However PPRA shall obtain the award information on the Reports to be submitted on the implementation of each procurement
20. | In this column the PE shall fill in the expected date for contract for contract award. For planning purposes this date shall be the determinant of the dates by which the preceding actions must be completed so that the award of contract is made by this date
21. | In this column the PE shall fill in the expected date for signing of the contract.
For More Information and Guidance, Contact
Chief Executive Officer,
Public Procurement Regulatory Authority
PPF Tower, 8th Floor
P.O. Box 49, Dar-es-Salaam
Tel. No. +255 22 2121236/7, 2133466
Fax. No. +255 22 2121238
E-mail: ceo@ppra.go.tz
Website: www.ppra.go.tz

## APP-GN97-EU
THE UNITED REPUBLIC OF TANZANIA
MINISTRY OF FOREIGN AFFAIRS AND EAST AFRICAN COOPERATION
GENERAL PROCUREMENT NOTICE (GPN)
FOR THE FINANCIAL YEAR 2019/2020
The Ministry of Foreign Affairs and East African Cooperation has set aside funds from its 2019/2020 budget towards the cost of procuring Goods, Works, Consultancy and Non Constuncy Services . The Ministry is now issuing the General Procument Notice (GPN) in accordance with the provisions of the PPA,2011 and reg 18 sub section (1)-(4) of Regulations 2013 for the purpose of informing potential and reputable, Suppliers, Consultants,Service Providers and Contractors. Announcement of the Specific Procument Notice is expected to follow the time frame indicated below. Potential and any additional information in favour of Prospective Bidders, Suppliers, Service Providers and Contractors may obtain further informations in the Office of the Secretary of the Tender Board. Ministry of Foreign Affairs and East African Cooperation, P. o. Box 2933, MTUMBA, DODOMA.
DESCRIPTION | TENDER NO. | LOT NO. | PROCUREMENT METHOD | PRE - QUALIFICATION |  |  | INVITATION FOR TENDERING |  | CONTRACT FINALIZATION | Plan vs. Actual
|  |  |  | Invitation Date | Closing-Opening | Notification of Applicants | Tender Invitation Date | Tender Closing-Opening | Notification of award
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
GOODS
Supply of Office Equipment | ME/013/2019-20/G/01 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Office Stationery and Computter consumables | ME/013/2019-20/G/02 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Purchase of Gifts and Prizes | ME/013/2019-20/G/03 |  | RT | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Spare Parts and Vehicle Accessories | ME/013/2019-20/G/04 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Office Furniture and Carpets | ME/013/2019-20/G/05 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of ICT Equipment | ME/013/2019-20/G/06 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Computer Software | ME/013/2019-20/G/07 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Fuel | ME/013/2019-20/G/08 |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Uniforms and Ceremonial dress | ME/013/2019 - 20/G/9 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Household Appliances, Kitchen Appliances, Utencils and Crockery | ME/013/2019-20/G/10 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Books, Reference and Periodicals | ME/013/2019-20/G/11 |  | NS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply and Installation Electrical Accessories | ME/013/2019-20/G/12 |  | NS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Purchase of TV and Radio | ME/013/2019-20/G/13 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Cleaning Materials and Sanitary | ME/013/2019-20/G/14 |  | NS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Supply of Sport Kit | ME/013/2019-20/G/15 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
NON CONSULTANCY SERVICES
Provision of Accommodation Service | ME/013/2019-20/NC/01 |  | RT | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Advertisement and Publication | ME/013/2019-20/NC/02 |  | RT | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Air Travel Tickets | ME/013/2019-20/NC/03 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Catering Services | ME/013/2019-20/NC/04 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Repair and Maintainance Service of motor vehicles | ME/013/2019-20/NC/05 |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Cleaning Service | ME/013/2019-20/NC/06 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Printing Services | ME/013/2019-20/NC/07 |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Hiring of Motor Vehicle Services | ME/013/2019-20/NC/08 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Security Service | ME/013/2019-20/NC/09 |  | FWC | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Internet and Connection Services | ME/013/2019-20/NC/10 |  | NS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Conference Services | ME/013/2019-20/NC/11 |  | RT | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
Provision of Clearing and Courier Services | ME/013/2019-20/NC/12 |  | SS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
WORKS
To undertake Periodic Repair and Maintenance of Building | ME/013/2019-20/W/01 |  | NS | N/A | N/A | N/A | N/A | N/A | N/A | Plan
Actual
FWC - Frame Work Contract .
RT- Restricted Tendering
SS - Single Source
NS - National Shopping
GPSA - Government Procurement and Service Agency.
N/A - Not Applicable
PERMANENT SECRETARY
MINISTRY OF FOREIGN AFFAIRS AND
EAST AFRICAN COOPERATION
Note on D26: GPSA

## APP-GN98-EU
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - EXTERNAL USE
Name of Procuring Entity: MINISTRY OF FOREIGN AFFAIRS AND EAST AFRICAN COOPERATION
FINANCIAL YEAR: 2019-2020
Description* | Basic Data |  |  |  |  | Request for Expression of Interest |  |  | Invitation of proposals and approval for award
| Tender No. | Lot Number | Procurement Method | Selection Method | Contract Type | Invitation Date | Closing-Opening | Notification Date | Consultant Proposals |  | Notification Date
[9 empty] | Invitation Date | Submission/ Opening Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Engagement of Consultant to Update Fixed Asset Register | ME/013/2019-20/C/01 |  | NCS | QCBS | Lumpsum | N/A | N/A | N/A | 22/08/2019 | 11/09/2019 | 2019-01-10
Engagement of individual Consultant to Establish and Manage Diaspora Database | ME/013/2019-20/C/02 |  | IS | CQ | Lumpsum | N/A | N/A | N/A | 17/09/2019 | 30/09/2019 | 14/10/2019
Engagement of Consultant to Design and Supervise of New Office Building at Government City- MTUMBA | ME/013/2019-20/C/03 |  | SS | CQ | Lumpsum | N/A | N/A | N/A | 26/09/2019 | 09/10/2019 | 23/10/2019